## User Management
Requirement - |  | User Management
| Open | 0
| In-Process | 2
| Pending | 3
| Complete | 2
| Cancel | 0
| New | 0
User Management | [11 empty] | Responsibility
No. | Catogories | Requirement Section | Types | Requirement ID | Requirement Specification | Priority | Story Points |  |  |  | Status
[7 empty] | BE | FE | Doc | Total |  | UI | DEV | TEST
1 | User Management | Log in(UC-1) | SR | [UserManagement_1] | Log in success, navigate to home page | 1 | 3 | 4 | 1 | 8 | Complete |  | DuyNM | GiapLH
2 | User Management | Log out(UC-2) | SR | [UserManagement_2] | Log out | 1 | 3 | 4 | 1 | 8 | Complete |  | DuyNM | GiapLH
3 | User Management | Sign-up(UC-3) | SR | [UserManagement_3] | Create account when sign up | 1 | 3 | 4 | 1 | 8 | In-Process |  | DuyNM | GiapLH
4 | User Management | Reset password(UC-4) | SR | [UserManagement_4] | Send confirmation by email then reset password | 1 | 3 | 4 | 1 | 8 | In-Process |  | DuyNM | DuyHDB
5 | User Management | View dasboard(UC-5) | SR | [UserManagement_5] | Dashboard for all role | 1 | 3 | 4 | 1 | 8 | Pending |  | DuyNM
6 | User Management | View courses by category(UC-6) | SR | [UserManagement_6] | List all courses by category | 1 | 3 | 4 | 1 | 8 | Pending |  | DuyNM | DuyHDB
7 | User Management | View courses by category filter(UC-7) | SR | [UserManagement_7] | List all courses by category filter | 1 | 3 | 4 | 1 | 8 | Pending |  | DuyNM | DuyHDB