## Master Schedule
Feature | Story | Status | EMD | BMD | Progress | Week 1 (28/6- 2/6) | Week 2 (3/6 - 9/6) | Week 3 (10/6 - 16/6) | Week 4 (17/6 - 23/6) | Week 5 (24/6 - 30/6) | Week 6 (1/7 - 6/7) | Week 7 (7/7 - 13/7) | Week 8 (14/7 - 21/7) | Week 9 (22/7 - 28/7) | Note
User Management | SRS, Usecase, ERD for User Management | In-Process | 7 | 0 | 0%
| Implement story Create User | Not-Start | 0 | 0 | 0%
| Implement story Import User | Not-Start | 0 | 0 | 0%
| Implement story Retrieve Users [List + Paging] | Not-Start | 0 | 0 | 0%
| Implement story Retrieve Users [Search + Filter] | Not-Start | 0 | 0 | 0%
| Implement story Update User | Not-Start | 0 | 0 | 0%
| Implement story Active User | Not-Start | 0 | 0 | 0%
| Implement story Deactive User | Not-Start | 0 | 0 | 0%
| Implement story Role-Permission User | Not-Start | 0 | 0 | 0%
| Implement story Authorize User | Not-Start | 0 | 0 | 0%
| Implement story Authenticate User | Not-Start | 0 | 0 | 0%
| Fix bug & Cover Task | Not-Start | 0 | 0 | 0%
Admin Management | SRS, Usecase, ERD for Category Management | In-Process | 7 | 0 | 0%
| Implement story View list Account | Not-Start | 0 | 0 | 0%
| Implement story Create (Role Student) | Not-Start | 0 | 0 | 0%
| Implement story Ban Account ( Role Student) | Not-Start | 0 | 0 | 0%
| Implement story Create ( Role Instructor ) | Not-Start | 0 | 0 | 0%
| Implement story Ban Account ( Role Instructor ) | Not-Start | 0 | 0 | 0%
| Implement story View List Category Request | Not-Start | 0 | 0 | 0%
| Implement story Approve Category Request | Not-Start | 0 | 0 | 0%
| Implement story Reject Category Request | Not-Start | 0 | 0 | 0%
| Implement story View List Course Request | Not-Start | 0 | 0 | 0%
| Implement story Approve Course Request | Not-Start | 0 | 0 | 0%
| Implement story Reject Course Request | Not-Start | 0 | 0 | 0%
| Implement story Dashboard of Admin | Not-Start | 0 | 0 | 0%
| Fix bug & Cover Task | Not-Start | 0 | 0 | 0%
Student Management | SRS, Usecase, ERD for Category Management | In-Process | 7 | 0 | 0%
| Implement story View Profile | Not-Start | 0 | 0 | 0%
| Implement story Enroll Course | Not-Start | 0 | 0 | 0%
| Implement story View Course Enrolled | Not-Start | 0 | 0 | 0%
| Implement story Edit Profile | Not-Start | 0 | 0 | 0%
| Implement story Edit Password | Not-Start | 0 | 0 | 0%
| Implement story View Certificate of Course complete | Not-Start | 0 | 0 | 0%
| Implement story Follow Instructor | Not-Start | 0 | 0 | 0%
| Implement story Unfollow Instructor | Not-Start | 0 | 0 | 0%
| Implement story View Notification for Student | Not-Start | 0 | 0 | 0%
| Fix bug & Cover Task | Not-Start | 0 | 0 | 0%
Instructor Management | SRS, Usecase, ERD for Category Management | In-Process | 7 | 0 | 0%
| Implement story View Profile | Not-Start | 0 | 0 | 0%
| Implement story Edit Profile | Not-Start | 0 | 0 | 0%
| Implement story Edit Password | Not-Start | 0 | 0 | 0%
| Implement story Update Course | Not-Start | 0 | 0 | 0%
| Implement story Close Course | Not-Start | 0 | 0 | 0%
| Implement story Create New Course | Not-Start | 0 | 0 | 0%
| Implement story Create New Category | Not-Start | 0 | 0 | 0%
| Implement story Dashboard of Instructor | Not-Start | 0 | 0 | 0%
| Implement story View List of Instructor's Course | Not-Start | 0 | 0 | 0%
| Implement story Payout | Not-Start | 0 | 0 | 0%
| Fix bug & Cover Task | Not-Start | 0 | 0 | 0%
Payment Management | SRS, Usecase, ERD for Category Management | In-Process | 7 | 0 | 0%
| Implement story History | Not-Start | 0 | 0 | 0%
| Implement story Credit Card ( VNPay, PayPal ) for Purchase | Not-Start | 0 | 0 | 0%
| Implement story Detail Course Order | Not-Start | 0 | 0 | 0%
| Fix bug & Cover Task | Not-Start | 0 | 0 | 0%
Category Management | SRS, Usecase, ERD for Category Management | In-Process | 7 | 0 | 0%
| Implement story Add Category | Not-Start | 0 | 0 | 0%
| Implement story Delete Category | Not-Start | 0 | 0 | 0%
| Implement story Edit Category | Not-Start | 0 | 0 | 0%
| Implement story View list of Category | Not-Start | 0 | 0 | 0%
| Implement story Search by Category | Not-Start | 0 | 0 | 0%
| Implement story Filter Category | Not-Start | 0 | 0 | 0%
| Fix bug & Cover Task | Not-Start | 0 | 0 | 0%
Course Management | SRS, Usecase, ERD for Course Management | In-Process | 7 | 0 | 0%
| Implement story Create Course | Not-Start | 0 | 0 | 0%
| Implement story Edit Course | Not-Start | 0 | 0 | 0%
| Implement story Add Syllabus | Not-Start | 0 | 0 | 0%
| Implement story Update Syllabus | Not-Start | 0 | 0 | 0%
| Implement story View Syllabus | Not-Start | 0 | 0 | 0%
| Implement story Delete Syllabus | Not-Start | 0 | 0 | 0%
| Implement story List Syllabus | Not-Start | 0 | 0 | 0%
| Implement story View List of Lecture | Not-Start | 0 | 0 | 0%
| Implement story Add Lecture | Not-Start | 0 | 0 | 0%
| Implement story Update Lecture | Not-Start | 0 | 0 | 0%
| Implement story Delete Lecture | Not-Start | 0 | 0 | 0%
| Fix bug & Cover Task | Not-Start | 0 | 0 | 0%
|  | Total Progress Actual |  |  | 0%
| Done | 0
| In-Process | 7
| Not-Start | 68
| Pending | 0

## User Management
Requirement - |  | User Management
| Open | 4
| In-Process | 11
| Pending | 0
| Complete | 0
| Cancel | 0
| New | 0
User Management | [11 empty] | Responsibility
No. | Catogories | Requirement Section | Types | Requirement ID | Requirement Specification | Priority | Story Points |  |  |  | Status
[7 empty] | BE | FE | Doc | Total |  | DEV
1 | User Management | View Homepage | SR | [User-Management_1] |  | 1 | 1 | 1 | 1 | 3 | Not implemented
2 | User Management | Update profile | SR | [User-Management_2] |  | 5 | 4 | 1 | 1 | 6 | Not implemented
3 | User Management | View and Search course | SR | [User-Management_3] |  | 3 | 2 | 2 | 1 | 5 | Not implemented
4 | User Management | View enrolled course | SR | [User-Management_4] |  | 1 | 1 | 3 | 1 | 5 | Not implemented
5 | User Management | View enrolled course | SR | [User-Management_5] |  | 2 | 1 | 2 | 1 | 4 | Not implemented
6 | User Management | View list of subscriptions | SR | [User-Management_6] |  | 3 | 1 | 2 | 0.5 | 2024-05-03 | Not implemented
7 | User Management | Search instructor | SR | [User-Management_7] |  | 4 | 2 | 2 | 0.5 | 2024-05-04 | Not implemented
8 | User Management | Purchase the course | SR | [User-Management_8] |  | 4 | 1 | 2 | 1 | 4 | Not implemented
9 | User Management | Enroll course | SR | [User-Management_9] |  | 4 | 1 | 2 | 1 | 4 | Not implemented
10 | User Management | Review course | SR | [User-Management_10] |  | 7 | 0.5 | 1 | 1 | 2024-05-02 | Not implemented
11 | User Management | Report course | SR | [User-Management_11] |  | 6 | 0.5 | 0.5 | 1 | 2 | Not implemented
12 | User Management | View Dashboard | SR | [User-Management_12] |  | 2 | 2 | 2 | 1 | 5 | Not implemented
13 | User Management | View course/ student analytics | SR | [User-Management_13] |  | 1 | 1 | 1 | 1 | 3 | Not implemented
14 | User Management | Payout | SR | [User-Management_14] |  | 2 | 1 | 1 | 1 | 3 | Not implemented
15 | User Management | Login | SR | [User-Management_15] |  | 3 | 1 | 1 | 1 | 3 | Not implemented
16 | User Management |  | SR | [User-Management_16] | [6 empty] | Not implemented
17 | User Management |  | SR | [User-Management_17] | [6 empty] | Not implemented
18 | User Management |  | SR | [User-Management_18] | [6 empty] | Not implemented
19 | User Management |  | SR | [User-Management_19] | [6 empty] | Not implemented
20 | User Management |  | SR | [User-Management_20] | [6 empty] | Not implemented
21 | User Management |  | SR | [User-Management_21] | [6 empty] | Not implemented
22 | User Management |  | SR | [User-Management_22] | [6 empty] | Not implemented
23 | User Management |  | SR | [User-Management_23] | [6 empty] | Not implemented
24 | User Management |  | SR | [User-Management_24] | [6 empty] | Not implemented
25 | User Management |  | SR | [User-Management_25] | [6 empty] | Not implemented
26 | User Management |  | SR | [User-Management_26] | [6 empty] | Not implemented
27 | User Management |  | SR | [User-Management_27] | [6 empty] | Not implemented
28 | User Management |  | SR | [User-Management_28] | [6 empty] | Not implemented
29 | User Management |  | SR | [User-Management_29] | [6 empty] | Not implemented
30 | User Management |  | SR | [User-Management_30] | [6 empty] | Not implemented

## Admin Management
Requirement - |  | User Management
| Open | 4
| In-Process | 11
| Pending | 0
| Complete | 0
| Cancel | 0
| New | 0
User Management | [11 empty] | Responsibility
No. | Catogories | Requirement Section | Types | Requirement ID | Requirement Specification | Priority | Story Points |  |  |  | Status
[7 empty] | BE | FE | Doc | Total |  | DEV
1 | User Management | View Homepage | SR | [User-Management_1] |  | 1 | 1 | 1 | 1 | 3 | Not implemented
2 | User Management | Update profile | SR | [User-Management_2] |  | 5 | 4 | 1 | 1 | 6 | Not implemented
3 | User Management | View and Search course | SR | [User-Management_3] |  | 3 | 2 | 2 | 1 | 5 | Not implemented
4 | User Management | View enrolled course | SR | [User-Management_4] |  | 1 | 1 | 3 | 1 | 5 | Not implemented
5 | User Management | View enrolled course | SR | [User-Management_5] |  | 2 | 1 | 2 | 1 | 4 | Not implemented
6 | User Management | View list of subscriptions | SR | [User-Management_6] |  | 3 | 1 | 2 | 0.5 | 2024-05-03 | Not implemented
7 | User Management | Search instructor | SR | [User-Management_7] |  | 4 | 2 | 2 | 0.5 | 2024-05-04 | Not implemented
8 | User Management | Purchase the course | SR | [User-Management_8] |  | 4 | 1 | 2 | 1 | 4 | Not implemented
9 | User Management | Enroll course | SR | [User-Management_9] |  | 4 | 1 | 2 | 1 | 4 | Not implemented
10 | User Management | Review course | SR | [User-Management_10] |  | 7 | 0.5 | 1 | 1 | 2024-05-02 | Not implemented
11 | User Management | Report course | SR | [User-Management_11] |  | 6 | 0.5 | 0.5 | 1 | 2 | Not implemented
12 | User Management | View Dashboard | SR | [User-Management_12] |  | 2 | 2 | 2 | 1 | 5 | Not implemented
13 | User Management | View course/ student analytics | SR | [User-Management_13] |  | 1 | 1 | 1 | 1 | 3 | Not implemented
14 | User Management | Payout | SR | [User-Management_14] |  | 2 | 1 | 1 | 1 | 3 | Not implemented
15 | User Management | Login | SR | [User-Management_15] |  | 3 | 1 | 1 | 1 | 3 | Not implemented
16 | User Management |  | SR | [User-Management_16] | [6 empty] | Not implemented
17 | User Management |  | SR | [User-Management_17] | [6 empty] | Not implemented
18 | User Management |  | SR | [User-Management_18] | [6 empty] | Not implemented
19 | User Management |  | SR | [User-Management_19] | [6 empty] | Not implemented
20 | User Management |  | SR | [User-Management_20] | [6 empty] | Not implemented
21 | User Management |  | SR | [User-Management_21] | [6 empty] | Not implemented
22 | User Management |  | SR | [User-Management_22] | [6 empty] | Not implemented
23 | User Management |  | SR | [User-Management_23] | [6 empty] | Not implemented
24 | User Management |  | SR | [User-Management_24] | [6 empty] | Not implemented
25 | User Management |  | SR | [User-Management_25] | [6 empty] | Not implemented
26 | User Management |  | SR | [User-Management_26] | [6 empty] | Not implemented
27 | User Management |  | SR | [User-Management_27] | [6 empty] | Not implemented
28 | User Management |  | SR | [User-Management_28] | [6 empty] | Not implemented
29 | User Management |  | SR | [User-Management_29] | [6 empty] | Not implemented
30 | User Management |  | SR | [User-Management_30] | [6 empty] | Not implemented

## Student Management
Requirement - |  | User Management
| Open | 4
| In-Process | 11
| Pending | 0
| Complete | 0
| Cancel | 0
| New | 0
User Management | [11 empty] | Responsibility
No. | Catogories | Requirement Section | Types | Requirement ID | Requirement Specification | Priority | Story Points |  |  |  | Status
[7 empty] | BE | FE | Doc | Total |  | DEV
1 | Studen Management |  | SR | [User-Management_1] | [6 empty] | Not implemented
2 | Studen Management |  | SR | [User-Management_2] | [6 empty] | Not implemented
3 | Studen Management |  | SR | [User-Management_3] | [6 empty] | Not implemented
4 | Studen Management |  | SR | [User-Management_4] | [6 empty] | Not implemented
5 | Studen Management |  | SR | [User-Management_5] | [6 empty] | Not implemented
6 | Studen Management |  | SR | [User-Management_6] | [6 empty] | Not implemented
7 | Studen Management |  | SR | [User-Management_7] | [6 empty] | Not implemented
8 | Studen Management |  | SR | [User-Management_8] | [6 empty] | Not implemented
9 | Studen Management |  | SR | [User-Management_9] | [6 empty] | Not implemented
10 | Studen Management |  | SR | [User-Management_10] | [6 empty] | Not implemented
11 | Studen Management |  | SR | [User-Management_11] | [6 empty] | Not implemented
12 | Studen Management |  | SR | [User-Management_12] | [6 empty] | Not implemented
13 | Studen Management |  | SR | [User-Management_13] | [6 empty] | Not implemented
14 | Studen Management |  | SR | [User-Management_14] | [6 empty] | Not implemented
15 | Studen Management |  | SR | [User-Management_15] | [6 empty] | Not implemented
16 | Studen Management |  | SR | [User-Management_16] | [6 empty] | Not implemented
17 | Studen Management |  | SR | [User-Management_17] | [6 empty] | Not implemented
18 | Studen Management |  | SR | [User-Management_18] | [6 empty] | Not implemented
19 | Studen Management |  | SR | [User-Management_19] | [6 empty] | Not implemented
20 | Studen Management |  | SR | [User-Management_20] | [6 empty] | Not implemented
21 | Studen Management |  | SR | [User-Management_21] | [6 empty] | Not implemented
22 | Studen Management |  | SR | [User-Management_22] | [6 empty] | Not implemented
23 | Studen Management |  | SR | [User-Management_23] | [6 empty] | Not implemented
24 | Studen Management |  | SR | [User-Management_24] | [6 empty] | Not implemented
25 | Studen Management |  | SR | [User-Management_25] | [6 empty] | Not implemented
26 | Studen Management |  | SR | [User-Management_26] | [6 empty] | Not implemented
27 | Studen Management |  | SR | [User-Management_27] | [6 empty] | Not implemented
28 | Studen Management |  | SR | [User-Management_28] | [6 empty] | Not implemented
29 | Studen Management |  | SR | [User-Management_29] | [6 empty] | Not implemented
30 | Studen Management |  | SR | [User-Management_30] | [6 empty] | Not implemented

## Instructor Management
Requirement - |  | User Management
| Open | 4
| In-Process | 11
| Pending | 0
| Complete | 0
| Cancel | 0
| New | 0
User Management | [11 empty] | Responsibility
No. | Catogories | Requirement Section | Types | Requirement ID | Requirement Specification | Priority | Story Points |  |  |  | Status
[7 empty] | BE | FE | Doc | Total |  | DEV
1 | Instructor Management |  | SR | [User-Management_1] | [6 empty] | Not implemented
2 | Instructor Management |  | SR | [User-Management_2] | [6 empty] | Not implemented
3 | Instructor Management |  | SR | [User-Management_3] | [6 empty] | Not implemented
4 | Instructor Management |  | SR | [User-Management_4] | [6 empty] | Not implemented
5 | Instructor Management |  | SR | [User-Management_5] | [6 empty] | Not implemented
6 | Instructor Management |  | SR | [User-Management_6] | [6 empty] | Not implemented
7 | Instructor Management |  | SR | [User-Management_7] | [6 empty] | Not implemented
8 | Instructor Management |  | SR | [User-Management_8] | [6 empty] | Not implemented
9 | Instructor Management |  | SR | [User-Management_9] | [6 empty] | Not implemented
10 | Instructor Management |  | SR | [User-Management_10] | [6 empty] | Not implemented
11 | Instructor Management |  | SR | [User-Management_11] | [6 empty] | Not implemented
12 | Instructor Management |  | SR | [User-Management_12] | [6 empty] | Not implemented
13 | Instructor Management |  | SR | [User-Management_13] | [6 empty] | Not implemented
14 | Instructor Management |  | SR | [User-Management_14] | [6 empty] | Not implemented
15 | Instructor Management |  | SR | [User-Management_15] | [6 empty] | Not implemented
16 | Instructor Management |  | SR | [User-Management_16] | [6 empty] | Not implemented
17 | Instructor Management |  | SR | [User-Management_17] | [6 empty] | Not implemented
18 | Instructor Management |  | SR | [User-Management_18] | [6 empty] | Not implemented
19 | Instructor Management |  | SR | [User-Management_19] | [6 empty] | Not implemented
20 | Instructor Management |  | SR | [User-Management_20] | [6 empty] | Not implemented
21 | Instructor Management |  | SR | [User-Management_21] | [6 empty] | Not implemented
22 | Instructor Management |  | SR | [User-Management_22] | [6 empty] | Not implemented
23 | Instructor Management |  | SR | [User-Management_23] | [6 empty] | Not implemented
24 | Instructor Management |  | SR | [User-Management_24] | [6 empty] | Not implemented
25 | Instructor Management |  | SR | [User-Management_25] | [6 empty] | Not implemented
26 | Instructor Management |  | SR | [User-Management_26] | [6 empty] | Not implemented
27 | Instructor Management |  | SR | [User-Management_27] | [6 empty] | Not implemented
28 | Instructor Management |  | SR | [User-Management_28] | [6 empty] | Not implemented
29 | Instructor Management |  | SR | [User-Management_29] | [6 empty] | Not implemented
30 | Instructor Management |  | SR | [User-Management_30] | [6 empty] | Not implemented

## Category Management
Requirement - |  | User Management
| Open | 4
| In-Process | 11
| Pending | 0
| Complete | 0
| Cancel | 0
| New | 0
User Management | [11 empty] | Responsibility
No. | Catogories | Requirement Section | Types | Requirement ID | Requirement Specification | Priority | Story Points |  |  |  | Status
[7 empty] | BE | FE | Doc | Total |  | DEV
1 | Category Management |  | SR |  | Create Course | 1 | 1 | 1 | 1 | 3 | Not implemented
2 | Category Management |  | SR |  | View Created Courses | 5 | 4 | 1 | 1 | 6 | Not implemented
3 | Category Management |  | SR |  | Edit Course | 3 | 2 | 2 | 1 | 5 | Not implemented
4 | Category Management |  | SR |  | Delete Course | 1 | 1 | 3 | 1 | 5 | Not implemented
5 | Category Management |  | SR |  | View Review of Created Course | 2 | 1 | 2 | 1 | 4 | Not implemented
6 | Category Management |  | SR |  | Search Course | 3 | 1 | 2 | 0.5 | 2024-05-03 | Not implemented
7 | Category Management |  | SR |  | View Purchased/Enrolled Courses | 4 | 2 | 2 | 0.5 | 2024-05-04 | Not implemented
8 | Category Management |  | SR |  | Buy Course | 4 | 1 | 2 | 1 | 4 | Not implemented
9 | Category Management |  | SR |  | Enroll Course | 4 | 1 | 2 | 1 | 4 | Not implemented
10 | Category Management |  | SR |  | Review Completed Course | 7 | 0.5 | 1 | 1 | 2024-05-02 | Not implemented
11 | Category Management |  | SR |  | Report Course | 6 | 0.5 | 0.5 | 1 | 2 | Not implemented
12 | Category Management |  | SR |  | Filter Course View by Category | 2 | 2 | 2 | 1 | 5 | Not implemented
13 | Category Management |  | SR |  | View All Courses | 1 | 1 | 1 | 1 | 3 | Not implemented
14 | Category Management |  | SR |  | View Course Detail | 2 | 1 | 1 | 1 | 3 | Not implemented
15 | Category Management |  | SR |  | Approve or Reject Create/Update Course Requests | 3 | 1 | 1 | 1 | 3 | Not implemented

## Payment Management
Requirement - |  | User Management
| Open | 4
| In-Process | 11
| Pending | 0
| Complete | 0
| Cancel | 0
| New | 0
User Management | [11 empty] | Responsibility
No. | Catogories | Requirement Section | Types | Requirement ID | Requirement Specification | Priority | Story Points |  |  |  | Status
[7 empty] | BE | FE | Doc | Total |  | DEV
1 | Payment Management | Instructor_CRUD Course | SR | [Payment Management_1] | Create Course | [5 empty] | Not implemented
2 | Payment Management | Instructor_CRUD Course | SR | [Payment Management_2] | View Created Courses | [5 empty] | Not implemented
3 | Payment Management | Instructor_CRUD Course | SR | [Payment Management_3] | Edit Course | [5 empty] | Not implemented
4 | Payment Management | Instructor_CRUD Course | SR | [Payment Management_4] | Delete Course | [5 empty] | Not implemented
5 | Payment Management | Instructor | SR | [Payment Management_5] | View Review of Created Course | [5 empty] | Not implemented
6 | Payment Management | Student_Course Actions | SR | [Payment Management_6] | Search Course | [5 empty] | Not implemented
7 | Payment Management | Student_Course Actions | SR | [Payment Management_7] | View Purchased/Enrolled Courses | [5 empty] | Not implemented
8 | Payment Management | Student_Course Actions | SR | [Payment Management_8] | Buy Course | [5 empty] | Not implemented
9 | Payment Management | Student_Course Actions | SR | [Payment Management_9] | Enroll Course | [5 empty] | Not implemented
10 | Payment Management | Student_Course Actions | SR | [Payment Management_10] | Review Completed Course | [5 empty] | Not implemented
11 | Payment Management | Student_Course Actions | SR | [Payment Management_11] | Report Course | [5 empty] | Not implemented
12 | Payment Management | Retrieve Courses | SR | [Payment Management_12] | Filter Course View by Category | [5 empty] | Not implemented
13 | Payment Management | Super Admin | SR | [Payment Management_13] | View All Courses | [5 empty] | Not implemented
14 | Payment Management | Super Admin | SR | [Payment Management_14] | View Course Detail | [5 empty] | Not implemented
15 | Payment Management | Super Admin | SR | [Payment Management_15] | Approve or Reject Create/Update Course Requests | [5 empty] | Not implemented

## Course Management
Requirement - |  | User Management
| Open | 4
| In-Process | 11
| Pending | 0
| Complete | 0
| Cancel | 0
| New | 0
User Management | [11 empty] | Responsibility
No. | Catogories | Requirement Section | Types | Requirement ID | Requirement Specification | Priority | Story Points |  |  |  | Status
[7 empty] | BE | FE | Doc | Total |  | DEV
1 | Course Management | Instructor_CRUD Course | SR | [Course Management_1] | Create Course | [5 empty] | Not implemented
2 | Course Management | Instructor_CRUD Course | SR | [Course Management_2] | View Created Courses | [5 empty] | Not implemented
3 | Course Management | Instructor_CRUD Course | SR | [Course Management_3] | Edit Course | [5 empty] | Not implemented
4 | Course Management | Instructor_CRUD Course | SR | [Course Management_4] | Delete Course | [5 empty] | Not implemented
5 | Course Management | Instructor | SR | [Course Management_5] | View Review of Created Course | [5 empty] | Not implemented
6 | Course Management | Student_Course Actions | SR | [Course Management_6] | Search Course | [5 empty] | Not implemented
7 | Course Management | Student_Course Actions | SR | [Course Management_7] | View Purchased/Enrolled Courses | [5 empty] | Not implemented
8 | Course Management | Student_Course Actions | SR | [Course Management_8] | Buy Course | [5 empty] | Not implemented
9 | Course Management | Student_Course Actions | SR | [Course Management_9] | Enroll Course | [5 empty] | Not implemented
10 | Course Management | Student_Course Actions | SR | [Course Management_10] | Review Completed Course | [5 empty] | Not implemented
11 | Course Management | Student_Course Actions | SR | [Course Management_11] | Report Course | [5 empty] | Not implemented
12 | Course Management | Retrieve Courses | SR | [Course Management_12] | Filter Course View by Category | [5 empty] | Not implemented
13 | Course Management | Super Admin | SR | [Course Management_13] | View All Courses | [5 empty] | Not implemented
14 | Course Management | Super Admin | SR | [Course Management_14] | View Course Detail | [5 empty] | Not implemented
15 | Course Management | Super Admin | SR | [Course Management_15] | Approve or Reject Create/Update Course Requests | [5 empty] | Not implemented
|  | Instructor |  |  | View Review
|  | Instructor |  |  | Create Course
|  | Instructor |  |  | Edit Course
|  | Instructor |  |  | Delete Course
|  | Instructor |  |  | View Self-Created Courses
|  | Student |  |  | Search Course
|  | Student |  |  | View Purchased/Enrolled Courses
|  | Student |  |  | Buy Course
|  | Student |  |  | Enroll Course
|  | Student |  |  | Review Course
|  | Student |  |  | Report Course
|  | All Users | *Retrieve/View User |  | Filter View Course by Category
|  | Admin |  |  | View list of Course
|  | Admin |  |  | View detail a Course
|  | Admin |  |  | Approve/ Reject create, edit course