## Student Management
Requirement - |  | Syllabus Management
| Open | 0
| In-Process | 21
| Pending | 0
| Complete | 0
| Cancel | 0
| New | 0
Syllabus Management | [13 empty] | Responsibility
No. | Catogories | Requirement Section | Types | Requirement ID | Requirement Specification | Priority | Story Points | [5 empty] | Status
[7 empty] | BE | FE | Doc | FE | Total | PIC |  | DEV
1 | StudentManagement | View Dashboard (UC-8) | SR | StudentManagement_1 | View Dashboard For Student | 1 | 1 | 1.5 | 1 |  | 3.5 | MinhPTQ | In-Process | PhuongHT
2 | StudentManagement | View Enrolled/Purchased Course (UC-9) | SR | StudentManagement_2 | View Enrolled/Purchased Course | 1 | 1 | 1.5 | 1 |  | 3.5 | ThienNT14 | In-Process | HaiNC
3 | StudentManagement | View Profile (UC-10) | SR | StudentManagement_3 | View Profile | 1 | 1 | 1.5 | 1 |  | 3.5 | AnhLD32 | In-Process | DuyNM
4 | StudentManagement | Edit Profile (UC-11) | SR | StudentManagement_4 | Edit Profile | 1 | 1 | 1.5 | 1 |  | 3.5 | MinhPTQ | In-Process | CanhNH
5 | StudentManagement | View Settings (UC-12) | SR | StudentManagement_5 | View Settings | 1 | 1 | 1.5 | 1 |  | 3.5 | AnhLD32 | In-Process | PhongNG
6 | StudentManagement | Edit Settings (UC-13) | SR | StudentManagement_6 | Edit Settings to display or undisplay information | 1 | 1 | 1.5 | 1 |  | 3.5 | ThienNT14 | In-Process | PhongNG
7 | StudentManagement | View Privacy (UC-14) | SR | StudentManagement_7 | View Privacy | 1 | 1 | 1.5 | 1 |  | 3.5 | AnhLD32 | In-Process | PhuongHT
8 | StudentManagement | Edit Privacy (UC-15) | SR | StudentManagement_8 | Edit Privacy | 1 | 1 | 1.5 | 1 |  | 3.5 | MinhPTQ | In-Process | HaiNC
9 | StudentManagement | View feedback history (UC-16) | SR | StudentManagement_9 | View feedback history | 1 | 1 | 1.5 | 1 |  | 3.5 | AnhLD32 | In-Process | DuyNM
10 | StudentManagement | Send feedback (UC-17) | SR | StudentManagement_10 | Send feedback | 1 | 1 | 1.5 | 1 |  | 3.5 |  | In-Process | CanhNH
11 | StudentManagement | Send request to become instructor(UC-18) | SR | StudentManagement_11 | Send request to becoming instructor | 1 | 1 | 1.5 | 1 |  | 3.5 | AnhLD32 | In-Process | PhongNG
12 | StudentManagement | View Course Details (UC-19) | SR | StudentManagement_12 | View more details of course | 1 | 1 | 1.5 | 1 |  | 3.5 | ThienNT14 | In-Process | PhuongHT
13 | StudentManagement | Comment course (UC-20) | SR | StudentManagement_13 | Comment course after finishing course | 1 | 1 | 1.5 | 1 |  | 3.5 |  | In-Process | HaiNC
14 | StudentManagement | Rating course (UC-21) | SR | StudentManagement_14 | Rating course after finishing course | 1 | 1 | 1.5 | 1 |  | 3.5 |  | In-Process | DuyNM
15 | StudentManagement | View tracking of the course (UC-22) | SR | StudentManagement_15 | View tracking of the course | 1 | 1 | 1.5 | 1 |  | 3.5 |  | In-Process | CanhNH
16 | StudentManagement | Studying in course (UC-23) | SR | StudentManagement_16 | Studying process in course | 1 | 1 | 1.5 | 1 |  | 3.5 |  | In-Process | PhongNG
17 | StudentManagement | View favorite course (UC-24) | SR | StudentManagement_17 | View list of favorite course | 1 | 1 | 1.5 | 1 |  | 3.5 |  | In-Process | PhuongHT
18 | StudentManagement | Save/Unsave favorite course (UC-25) | SR | StudentManagement_18 | Save/Unsave favorite course to list | 1 | 1 | 1.5 | 1 |  | 3.5 |  | In-Process | HaiNC
19 | StudentManagement | View Notification (UC-26) | SR | StudentManagement_19 | View Notification For Student | 1 | 1 | 1.5 | 1 |  | 3.5 |  | In-Process | DuyNM
20 | StudentManagement | Follow/Unfollow instructor (UC-27) | SR | StudentManagement_20 | Follow/Unfollow instructor | 1 | 1 | 1.5 | 1 |  | 3.5 |  | In-Process | CanhNH
21 | StudentManagement | View Follower (UC-28) | SR | StudentManagement_21 | View Follower | 1 | 1 | 1.5 | 1 |  | 3.5 |  | In-Process | PhongNG
#REF!