## Master Schedule
Feature | Story | Status | EMD | BMD | Progress | Week 1 (28/5 - 2/6) | Week 2 (3/6 - 7/6) | Week 3 (10/6 - 16/6) | Week 4 (17/6 - 21/6) | Week 5 (24/6 - 30/6) | Week 6 (1/7 - 5/7) | Week 7 (8/7 - 14/7) | Week 8 (15/7-19/7) | Week 9 (22/7-28/7) | Week 10 (29/7-2/8) | Note
User Management | SRS, Usecase, ERD for User Management | Done | 20 | 20 | 100% | 5 | 5 | 5 | 5
| Implement story Login | Done | 7 | 7 | 100% |  | 4 | 3
| Implement story Logout | Done | 5 | 5 | 100% |  | 3 |  | 2
| Implement story View Dashboard | Not-Start | 0 | 0 | #DIV/0!
| Implement story Retrives Course By Category List | Not-Start | 0 | 0 | #DIV/0!
| Implement story Retrives Course By Category Filter | Not-Start | 0 | 0 | #DIV/0!
| Implement story Retrives Course By Sub-Category in Category List | Not-Start | 0 | 0 | #DIV/0!
| Implement story Retrives Course By Sub-Category in Category Filter | Not-Start | 0 | 0 | #DIV/0!
| Fix bug & Cover Task | Not-Start | 0 | 0 | #DIV/0!
Student Management | SRS, Usecase, ERD for Student Management | Done | 20 | 20 | 100% | 5 | 5 | 5 | 5
| Implement story Authorization Student | In-Progress | 6 | 5 | 83.33% |  |  | 2 |  | 4
| Implement story Role-Permission For Student | Not-Start | 0 | 0 | #DIV/0!
| Implement story View Dashboard For Student | Not-Start | 0 | 0 | #DIV/0!
| Implement story Erroll in the Course | In-Progress | 4 | 3 | 75% |  |  | 2 |  | 2
| Implement Story View Profile | In-Progress | 6 | 5 | 83.33% |  |  | 2 |  | 2 | 2
| Implement Story Edit Profile | In-Progress | 6 | 5 | 83.33% |  |  | 2 |  | 2 | 2
| Implement Story View Setting | Not-Start | 0 | 0 | #DIV/0!
| Implement Story Edit Setting | Not-Start | 0 | 0 | #DIV/0!
| Implement Story View Privacy | In-Progress | 0 | 0 | #DIV/0!
| Implement Story Edit Privacy | In-Progress | 0 | 0 | #DIV/0!
| Implement story Feedback Course | In-Progress | 0 | 0 | #DIV/0!
| Implement story Send request to become Instructor | Not-Start | 0 | 0 | #DIV/0!
| Implement story view Course | In-Progress | 6 | 3 | 50% |  | 3 |  |  | 3
| implement story Study in Course | In-Progress | 6 | 3 | 50% |  |  |  | 2 | 4
| Implement story Save/Delete Favorite Course | Not-Start | 0 | 0 | #DIV/0!
| Implement story View tracking of the course | Not-Start | 0 | 0 | #DIV/0!
| Implement story View Notification For Student | Not-Start | 0 | 0 | #DIV/0!
| Implement story Follow/Unfollow Instructor | Not-Start | 0 | 0 | #DIV/0!
| Implement story Commentcourse | In-Progress | 0 | 0 | #DIV/0!
| Implement story Rating course | Not-Start | 0 | 0 | #DIV/0!
| Fix bug & Cover Task | Not-Start | 0 | 0 | #DIV/0!
Instructor Management | SRS, Usecase, ERD for Instructor Management | Done | 20 | 20 | 100% | 5 | 5 | 5 | 5
| Implement story Authorization Instructor | In-Progress | 5 | 4 | 80% |  |  |  |  | 3 | 2
| Implement story Role-Permission For Instructor | In-Progress | 5 | 4 | 80% |  |  |  |  | 3 | 2
| Implement story View Dashboard For Instructor | Not-Start | 0 | 0 | #DIV/0!
| Implement Story View Homepage | In-Progress | 6 | 3 | 50% |  |  |  | 2 | 2 | 2
| Implement Story extends Student Management | Not-Start | 0 | 0 | #DIV/0!
| Implement Story View Dashboard Course analytics | Not-Start | 0 | 0 | #DIV/0!
| Implement Story View Dashboard Student analytics | Not-Start | 0 | 0 | #DIV/0!
| Implement Story View Earning | Not-Start | 0 | 0 | #DIV/0!
| Implement Story PayOut | Not-Start | 0 | 0 | #DIV/0!
| Implement story View Notification For Instructor | Not-Start | 0 | 0 | #DIV/0!
| Fix bug & Cover Task | Not-Start | 0 | 0 | #DIV/0!
Admin Management | SRS, Usecase, ERD for Admin Management | Done | 20 | 20 | 100% | 5 | 5 | 5 | 5
| Implement story Authorization Admin | Not-Start | 0 | 0 | #DIV/0!
| Implement story Role-Permission For Admin | Not-Start | 0 | 0 | #DIV/0!
| Implement story View Dashboard For Admin | Not-Start | 0 | 0 | #DIV/0!
| Implement story View List Of Students | Not-Start | 0 | 0 | #DIV/0!
| Implement story View List Of Instructors | Not-Start | 0 | 0 | #DIV/0!
| Implement story Block/Unblock Students, Instructors | Not-Start | 0 | 0 | #DIV/0!
| Implement story Approve Student To Instructor | Not-Start | 0 | 0 | #DIV/0!
| Implement story Reject Student To Instructor | Not-Start | 0 | 0 | #DIV/0!
| Implement story View List Of Courses | Not-Start | 0 | 0 | #DIV/0!
| Implement story Review course | Not-Start | 0 | 0 | #DIV/0!
| Implement story Approve course | Not-Start | 0 | 0 | #DIV/0!
| Implement story Reject course | Not-Start | 0 | 0 | #DIV/0!
| Implement story Block/Unblock course | Not-Start | 0 | 0 | #DIV/0!
| Implement story Display/Undisplay comments for block's users | Not-Start | 0 | 0 | #DIV/0!
| Implement story View List Of Feedbacks from User | Not-Start | 0 | 0 | #DIV/0!
| Fix bug & Cover Task | Not-Start | 0 | 0 | #DIV/0!
Category Management | SRS, Usecase, ERD for Category Management | Done | 20 | 20 | 100% | 5 | 5 | 5 | 5
| Implement story Create categories | Not-Start | 0 | 0 | #DIV/0!
| Implement story View Categories | In-Progress | 5 | 3 | 60% |  |  |  | 2 |  | 3
| Implement story Update Categories | Not-Start | 0 | 0 | #DIV/0!
| Implement story Delete Categories | Not-Start | 0 | 0 | #DIV/0!
| Implement story View sub-categories from main category | Not-Start | 0 | 0 | #DIV/0!
| Implement story Create sub-categories from main category | Not-Start | 0 | 0 | #DIV/0!
| Implement story Update sub-categories from main category | Not-Start | 0 | 0 | #DIV/0!
| Implement story Delete sub-categories from main category | Not-Start | 0 | 0 | #DIV/0!
| Fix bug & Cover Task | Not-Start | 0 | 0 | #DIV/0!
Course Management | SRS, Usecase, ERD for Course Management | Done | 20 | 20 | 100% | 5 | 5 | 5 | 5
| Implement story View list course | In-Progress | 5 | 3 | 60% |  |  |  | 2 |  | 3
| Implement story Create course | In-Progress | 2.5 | 0 | 0% |  |  |  |  | 2.5
| Implement story Update course | In-Progress | 2.5 | 0 | 0% |  |  |  |  | 2.5
| Implement story Delete course | In-Progress | 2.5 | 0 | 0% |  |  |  |  | 2.5
| Implement story View chapters of course | In-Progress | 5 | 3 | 60% |  |  |  | 2 | 3
| Implement story Create chapters of course | In-Progress | 2.5 | 0 | 0% |  |  |  |  | 2.5
| Implement story Update chapters of course | In-Progress | 2.5 | 0 | 0% |  |  |  |  | 2.5
| Implement story Delete chapters of course | In-Progress | 2.5 | 0 | 0% |  |  |  |  | 2.5
| Implement story View quizzes of chapters | In-Progress | 5 | 3 | 60% |  |  | 2 |  | 3
| Implement story Create quizzes of chapters | In-Progress | 2.5 | 0 | 0% | [5 empty] | 2.5
| Implement story Update quizzes of chapters | In-Progress | 2.5 | 0 | 0% | [5 empty] | 2.5
| Implement story Delete quizzes of chapters | In-Progress | 2.5 | 0 | 0% | [5 empty] | 2.5
| Implement story View questions of quizzes | In-Progress | 5 | 3 | 60% |  |  |  | 2 | 3
| Implement story Create questions of quizzes | In-Progress | 2.5 | 0 | 0% | [5 empty] | 2.5
| Implement story Update questions of quizzes | In-Progress | 2.5 | 0 | 0% | [5 empty] | 2.5
| Implement story Delete answers of questions | In-Progress | 2.5 | 0 | 0% | [5 empty] | 2.5
| Implement story View answers of questions | In-Progress | 5 | 3 | 60% |  |  | 2 |  | 3
| Implement story Create answers of questions | In-Progress | 2.5 | 0 | 0% | [5 empty] | 2.5
| Implement story Update answers of questions | In-Progress | 2.5 | 0 | 0% | [5 empty] | 2.5
| Implement story Delete answers of questions | In-Progress | 2.5 | 0 | 0% | [5 empty] | 2.5
| Implement story View certificate of course | In-Progress | 5 | 3 | 60% |  |  |  | 2 |  | 3
| Implement story Create certificate of course | In-Progress | 2.5 | 0 | 0% |  |  |  |  | 2.5
| Implement story Update certificate of course | In-Progress | 2.5 | 0 | 0% |  |  |  |  | 2.5
| Implement story View lecture of course | In-Progress | 5 | 3 | 60% |  |  |  | 2 |  | 3
| Implement story Create lecture of course | Not-Start | 0 | 0 | #DIV/0!
| Implement story Update lecture of course | Not-Start | 0 | 0 | #DIV/0!
| Implement story Delete lecture of course | Not-Start | 0 | 0 | #DIV/0!
| Implement story Submit course for approval | In-Progress | 5 | 3 | 60% |  |  |  | 2 |  | 3
| Implement story Report course | Not-Start | 0 | 0 | #DIV/0!
| Fix bug & Cover Task | Not-Start | 0 | 0 | #DIV/0!
Transaction Management | SRS, Usecase, ERD for Transaction Management | Done | 20 | 20 | 100% | 5 | 5 | 5 | 5
| Implement story View Wallet | Not-Start | 0 | 0 | #DIV/0!
| Implement story View Cart | Not-Start | 0 | 0 | #DIV/0!
| Implement story Add to Cart | Not-Start | 0 | 0 | #DIV/0!
| Implement story Delete Course in Cart | Not-Start | 0 | 0 | #DIV/0!
| Implement story Purchase Orders | Not-Start | 0 | 0 | #DIV/0!
| Implement story View Transaction History | Not-Start | 0 | 0 | #DIV/0!
| Implement story Earning Affiliate marketing For User | Not-Start | 0 | 0 | #DIV/0!
| Implement story Create Commissions for Instructor | Not-Start | 0 | 0 | #DIV/0!
| Implement story Deposit Money to Wallet | Not-Start | 0 | 0 | #DIV/0!
| Fix bug & Cover Task | Not-Start | 0 | 0 | #DIV/0!
|  | Total Progress Actual |  |  | #DIV/0! | 35 | 45 | 50 | 55 | 57 | 47.5 | 0 | 0 | 0 | 0
| Done | 6
| Not-Start | 41
| In-Progress | 13
| Pending | 0