## Sprint Info
| Planning - Forecast |  |  |  |  | Actual
[5 empty] | PIC | Point | Release Point | Total ID
| Point Total |  | Points |  | MinhNHL | 0 | 0 | 0
| Working days of developer |  | Coding (day) |  | HungLC | 0 | 0 | 0
| Sprint 1 |  |  |  | HuyVH | 0 | 0 | 0
| (Forecast - Plan) Point Total | 0 | Points |  | SyNNV | 0 | 0 | 0
| Working days of developer | 8 | Coding (day) |  | QuanNM | 0 | 0 | 0
| (Forecast - Plan) AVG points/Member/Sprint | 0.0 | Points |  | DuyNM | 0 | 0 | 0
[5 empty] | PhuongHT | 0 | 0 | 0
[5 empty] | CanhNH | 0 | 0 | 0
[5 empty] | PhongNG | 0 | 0 | 0
[5 empty] | HaiNC | 0 | 0 | 0
[5 empty] | Total | 0 | 0 | 0
[6 empty] | Total |  | 95.5
No. | Module | Story | Description | Sprint | Status | PIC | DueDate | Point
1 | FE | [FrontEnd-Dev] Authorized Instructor | Design Components for Authorized Instructor | 3 | Process | DuyNM | 2024-07-05 | 4
2 | FE | [FrontEnd-Dev] Role-Permission For Instructor | Design Components for Role-Permission for Instructor | 3 | Process | MinhNHL | 2024-07-05 | 4
3 | FE | [FontEnd-Dev] Homepage | Design Components for HomePage | 3 | Process | QuanNM | 2024-07-05 | 4
4 | FE | [FontEnd-Dev] View Categories | Design Components for View Categories | 3 | Process | CanhNH | 2024-07-05 | 4
5 | FE | [FrontEnd-Dev] View List Course | Design Components for View List Course | 3 | Process | HaiNC | 2024-07-05 | 4
6 | FE | [FontEnd-Dev] View chapters of courses | Design Components for View chapters of courses | 3 | Process | HungLC | 2024-07-05 | 4
7 | FE | [FrontEnd-Dev] View quizzes of Chapters | Design Components for View quizzes of Chapters | 3 | Process | SyNNV | 2024-07-05 | 4
8 | FE | [FontEnd-Dev] View questions of quizzes | Design Components for View questions of quizzes | 3 | Process | DuyNM | 2024-07-05 | 4
9 | FE | [FrontEnd-Dev] View Answer of questions | Design Component for View Answer of questions | 3 | Process | MinhNHL | 2024-07-05 | 4
10 | FE | [FrontEnd-Dev] View certificate of courses | Design Components for View certificate of Courses | 3 | Process | QuanNM | 2024-07-05 | 4
11 | FE | [FrontEnd-Dev] View lecture of courses | Design Components for View lecture of courses | 3 | Process | CanhNH | 2024-07-05 | 4
12 | FE | [FontEnd-Dev] Submit course for approval | Design Components for Submit course for approval | 3 | Process | HaiNC | 2024-07-05 | 4
13 | BE | [BackEnd-Dev] View List Course | Write API for View List Course | 3 | Process | PhongNG | 2024-07-05 | 2.5
14 | BE | [BackEnd-Dev] Create Course | Write API for Create Course | 3 | Process | PhuongHT | 2024-07-05 | 2.5
15 | BE | [BackEnd-Dev] Update Course | Write API for Update Course | 3 | Process | HuyVH | 2024-07-05 | 2.5
16 | BE | [BackEnd-Dev] Delete Course | Write API for Delete Course | 3 | Process | PhongNG | 2024-07-05 | 2.5
17 | BE | [BackEnd-Dev] View Chapter of Course | Write API for View Chapter of Course | 3 | Process | PhuongHT | 2024-07-05 | 2.5
18 | BE | [BackEnd-Dev] Create Chapter of Course | Write API for Create Chapter of Course | 3 | Process | HuyVH | 2024-07-05 | 2.5
19 | BE | [BackEnd-Dev] Update Chapter of Course | Write API for Update Chapter of Course | 3 | Process | PhongNG | 2024-07-05 | 2.5
20 | BE | [BackEnd-Dev] Delete Chapter of Course | Write API for Delete Chapter of Course | 3 | Process | PhuongHT | 2024-07-05 | 2.5
21 | BE | [BackEnd-Dev] View Quizzes of Chapters | Write API for View Quizzes of Chapters | 3 | Process | HuyVH | 2024-07-05 | 2.5
22 | BE | [BackEnd-Dev] Create Quizzes of Chapters | Write API for Create Quizzes of Chapters | 3 | Process | PhongNG | 2024-07-05 | 2.5
23 | BE | [BackEnd-Dev] Update Quizzes of Chapters | Write API for Update Quizzes of Chapters | 3 | Process | PhuongHT | 2024-07-05 | 2.5
24 | BE | [BackEnd-Dev] Delete Quizzes of Chapters | Write API for Delete Quizzes of Chapters | 3 | Process | HuyVH | 2024-07-05 | 2.5
25 | BE | [BackEnd-Dev] View Questions of Quizzes | Write API for View Questions of Quizzes | 3 | Process | PhongNG | 2024-07-05 | 2.5
26 | BE | [BackEnd-Dev] Create Questions of Quizzes | Write API for Create Questions of Quizzes | 3 | Process | PhuongHT | 2024-07-05 | 2.5
27 | BE | [BackEnd-Dev] Update Questions of Quizzes | Write API for Update Questions of Quizzes | 3 | Process | HuyVH | 2024-07-05 | 2.5
28 | BE | [BackEnd-Dev] Delete Questions of Quizzes | Write API for Delete Questions of Quizzes | 3 | Process | PhongNG | 2024-07-05 | 2.5
29 | BE | [BackEnd-Dev] View Certificate of Course | Write API for View Certificate of Course | 3 | Process | PhuongHT | 2024-07-05 | 2.5
30 | BE | [BackEnd-Dev] Create Certificate of Course | Write API for Create Certificate of Course | 3 | Process | HuyVH | 2024-07-05 | 2.5
31 | BE | [BackEnd-Dev] Update Certificate of Course | Write API for Update Certificate of Course | 3 | Process | PhongNG | 2024-07-05 | 2.5