## Master Schedule
Feature | Story | Status | EMD | BMD | Progress | Week 1 (3/10 - 7/10) | Week 2 (10/10 - 14/10) | Week 3 (17/10 - 21/10) | Week 4 (24/10 - 28/10) | Week 5 (31/10 - 4/11) | Week 6 (7/11 - 11/11) | Week 7 (14/11 - 18/11) | Week 8 (21/11-25/11) | Note
User Management | SRS, Usecase, ERD for User Management | In-Process | 24.00 | 12.00 | 50%
| Implement story Create & Import User | Not-Start | 6.00 | 0.00 | 0%
| Implement story Retrieve Users [List + Paging] & [Search + Filter] | Not-Start | 8.50 | 4.50 | 53%
| Implement story Update User/Active/Deactive User/Delete | Not-Start | 4.25 | 0.00 | 0%
| Implement story Role-Permission, Authenticate & Authorize User | Not-Start | 11.50 | 9.00 | 78%
| Fix bug & Cover Task | Not-Start | 19.25 | 0.00 | 0%
Course Management | SRS, Usecase, ERD for Course Management | In-Process | 24.00 | 24.00 | 100%
| Implement story Create Course | Not-Start | 9.00 | 5.00 | 56%
| Implement story Update and View Syllabus | Not-Start | 6.50 | 2.00 | 31%
| Implement story List Syllabus | Not-Start | 7.00 | 3.00 | 43%
| Implement story CRUD Metadata Output Standard/Delivery Type, Training Syllabus Material | Not-Start | 10.50 | 5.00 | 48%
| Fix bug & Cover Task | Not-Start | 15.00 | 0.00 | 0%
|  | Total Progress Actual |  |  | 31%

## User Management
Requirement - |  | User Management
| Open | 4
| In-Process | 11
| Pending | 0
| Complete | 0
| Cancel | 0
| New | 0
User Management | [11 empty] | Responsibility
No. | Catogories | Requirement Section | Types | Requirement ID | Requirement Specification | Priority | Story Points |  |  |  | Status
[7 empty] | BE | FE | Doc | Total |  | DEV
1 | User Management | View Homepage | SR | [User-Management_1] |  | 1 | 1 | 1 | 1 | 3 | Not-Start
2 | User Management | Update profile | SR | [User-Management_2] |  | 5 | 4 | 1 | 1 | 6 | In-Process
3 | User Management | View and Search course | SR | [User-Management_3] |  | 3 | 2 | 2 | 1 | 5 | In-Process
4 | User Management | View enrolled course | SR | [User-Management_4] |  | 1 | 1 | 3 | 1 | 5 | In-Process
5 | User Management | View enrolled course | SR | [User-Management_5] |  | 2 | 1 | 2 | 1 | 4 | In-Process
6 | User Management | View list of subscriptions | SR | [User-Management_6] |  | 3 | 1 | 2 | 0.5 | 2024-05-03 | In-Process
7 | User Management | Search instructor | SR | [User-Management_7] |  | 4 | 2 | 2 | 0.5 | 2024-05-04 | In-Process
8 | User Management | Purchase the course | SR | [User-Management_8] |  | 4 | 1 | 2 | 1 | 4 | In-Process
9 | User Management | Enroll course | SR | [User-Management_9] |  | 4 | 1 | 2 | 1 | 4 | In-Process
10 | User Management | Review course | SR | [User-Management_10] |  | 7 | 0.5 | 1 | 1 | 2024-05-02 | In-Process
11 | User Management | Report course | SR | [User-Management_11] |  | 6 | 0.5 | 0.5 | 1 | 2 | In-Process
12 | User Management | View Dashboard | SR | [User-Management_12] |  | 2 | 2 | 2 | 1 | 5 | In-Process
13 | User Management | View course/ student analytics | SR | [User-Management_13] |  | 1 | 1 | 1 | 1 | 3 | In-Process
14 | User Management | Payout | SR | [User-Management_14] |  | 2 | 1 | 1 | 1 | 3 | In-Process
15 | User Management | Login | SR | [User-Management_15] |  | 3 | 1 | 1 | 1 | 3 | In-Process
16 | User Management |  | SR | [User-Management_16]
17 | User Management |  | SR | [User-Management_17]
18 | User Management |  | SR | [User-Management_18]
19 | User Management |  | SR | [User-Management_19]
20 | User Management |  | SR | [User-Management_20]
21 | User Management |  | SR | [User-Management_21]
22 | User Management |  | SR | [User-Management_22]
23 | User Management |  | SR | [User-Management_23]
24 | User Management |  | SR | [User-Management_24]
25 | User Management |  | SR | [User-Management_25]
26 | User Management |  | SR | [User-Management_26]
27 | User Management |  | SR | [User-Management_27]
28 | User Management |  | SR | [User-Management_28]
29 | User Management |  | SR | [User-Management_29]
30 | User Management |  | SR | [User-Management_30]

## Course Management
Requirement - |  | User Management
| Open | 4
| In-Process | 11
| Pending | 0
| Complete | 0
| Cancel | 0
| New | 0
User Management | [11 empty] | Responsibility
No. | Catogories | Requirement Section | Types | Requirement ID | Requirement Specification | Priority | Story Points |  |  |  | Status
[7 empty] | BE | FE | Doc | Total |  | DEV
1 | Course Management | Instructor_CRUD Course | SR | [Course Management_1] | Create Course | 1 | 1 | 1 | 1 | 3 | Not implemented
2 | Course Management | Instructor_CRUD Course | SR | [Course Management_2] | View Created Courses | 5 | 4 | 1 | 1 | 6 | Not implemented
3 | Course Management | Instructor_CRUD Course | SR | [Course Management_3] | Edit Course | 3 | 2 | 2 | 1 | 5 | Not implemented
4 | Course Management | Instructor_CRUD Course | SR | [Course Management_4] | Delete Course | 1 | 1 | 3 | 1 | 5 | Not implemented
5 | Course Management | Instructor | SR | [Course Management_5] | View Review of Created Course | 2 | 1 | 2 | 1 | 4 | Not implemented
6 | Course Management | Student_Course Actions | SR | [Course Management_6] | Search Course | 3 | 1 | 2 | 0.5 | 2024-05-03 | Not implemented
7 | Course Management | Student_Course Actions | SR | [Course Management_7] | View Purchased/Enrolled Courses | 4 | 2 | 2 | 0.5 | 2024-05-04 | Not implemented
8 | Course Management | Student_Course Actions | SR | [Course Management_8] | Buy Course | 4 | 1 | 2 | 1 | 4 | Not implemented
9 | Course Management | Student_Course Actions | SR | [Course Management_9] | Enroll Course | 4 | 1 | 2 | 1 | 4 | Not implemented
10 | Course Management | Student_Course Actions | SR | [Course Management_10] | Review Completed Course | 7 | 0.5 | 1 | 1 | 2024-05-02 | Not implemented
11 | Course Management | Student_Course Actions | SR | [Course Management_11] | Report Course | 6 | 0.5 | 0.5 | 1 | 2 | Not implemented
12 | Course Management | Retrieve Courses | SR | [Course Management_12] | Filter Course View by Category | 2 | 2 | 2 | 1 | 5 | Not implemented
13 | Course Management | Super Admin | SR | [Course Management_13] | View All Courses | 1 | 1 | 1 | 1 | 3 | Not implemented
14 | Course Management | Super Admin | SR | [Course Management_14] | View Course Detail | 2 | 1 | 1 | 1 | 3 | Not implemented
15 | Course Management | Super Admin | SR | [Course Management_15] | Approve or Reject Create/Update Course Requests | 3 | 1 | 1 | 1 | 3 | Not implemented
|  | Instructor |  |  | View Review
|  | Instructor |  |  | Create Course
|  | Instructor |  |  | Edit Course
|  | Instructor |  |  | Delete Course
|  | Instructor |  |  | View Self-Created Courses
|  | Student |  |  | Search Course
|  | Student |  |  | View Purchased/Enrolled Courses
|  | Student |  |  | Buy Course
|  | Student |  |  | Enroll Course
|  | Student |  |  | Review Course
|  | Student |  |  | Report Course
|  | All Users | *Retrieve/View User |  | Filter View Course by Category
|  | Admin |  |  | View list of Course
|  | Admin |  |  | View detail a Course
|  | Admin |  |  | Approve/ Reject create, edit course