## Sprint Info
| Planning - Forecast |  |  |  |  | Actual
[5 empty] | PIC | Point | Release Point | Total ID
| Point Total |  | Points |  | MinhNHL | 0 | 0 | 0
| Working days of developer |  | Coding (day) |  | HungLC | 0 | 0 | 0
| Sprint 1 |  |  |  | HuyVH | 0 | 0 | 0
| (Forecast - Plan) Point Total | 0 | Points |  | SyNNV | 0 | 0 | 0
| Working days of developer | 8 | Coding (day) |  | QuanNM | 0 | 0 | 0
| (Forecast - Plan) AVG points/Member/Sprint | 0.0 | Points |  | Total | 0 | 0 | 0
[6 empty] | Total |  | 0
No. | Module | Story | Description | Sprint | Status | PIC | DueDate | Point
1 | Basic Design | [Dashboard] Dashboard | basic design & common components of dashboard UI for guest, student, instructor | 1 | In-progress |  | 06-Jun
2 | Basic Design | [General Users] List of courses | basic design & common components of list of courses | 1 | In-progress |  | 06-Jun
3 | Basic Design | [General Users] Course detail | basic design & common components of course detail | 1 | In-progress |  | 06-Jun
4 | Basic Design | [General Users] Login | basic design & common components of login | 1 | In-progress |  | 06-Jun
5 | Basic Design | [General Users] Register | basic design & common components of register for Student and Instructor | 1 | In-progress |  | 06-Jun
6 | Basic Design | [General Users ] Forgot Password | basic design & common components of forgot password | 1 | In-progress |  | 06-Jun
7 | Basic Design | [General Users ] Update Profile | basic design & common components of update profile | 1 | In-progress |  | 06-Jun
8 | Basic Design | [Courses Management] List of courses | basic design & common components of list of courses | 1 | In-progress |  | 06-Jun
9 | Basic Design | [Courses Management] Course detail | basic design & common components of course detail | 1 | In-progress |  | 06-Jun
10 | Basic Design | [Courses Management] Course update | basic design & common components of creating or editing courses | 1 | In-progress |  | 06-Jun
11 | Basic Design | [Courses Management] List of reviews | basic design & common components of list of courses' reviews | 1 | In-progress |  | 06-Jun
12 | Basic Design | [User Management] List of users | basic design & common components of list of user | 1 | In-progress |  | 06-Jun
13 | Basic Design | [User Management] User detail | basic design & common components of list of detail | 1 | In-progress |  | 06-Jun
14 | Basic Design | [User Management] User update | basic design & common components of creating or editing users | 1 | In-progress |  | 06-Jun
15 | Basic Design | [Student] List of courses | basic design & common components of list of purchased courses | 1 | In-progress |  | 06-Jun
16 | Basic Design | [Student] Purchase courses | basic design & common components of purchasing a course | 1 | In-progress |  | 06-Jun
17 | Basic Design | [Student] Course review | basic design & common components of course review form | 1 | In-progress |  | 06-Jun
18 | Basic Design | [Instructor] List of courses | basic design & common components of list of courses | 1 | In-progress |  | 06-Jun
19 | Basic Design | [Instructor] Course update | basic design & common components of creating or updating course | 1 | In-progress |  | 06-Jun
20 | Basic Design | [Instructor] List of review | basic design & common components of list of courses's review | 1 | In-progress |  | 06-Jun
23 | Basic Design | [Categories Management] List of categories | basic design & common components of categories | 1 | In-progress |  | 06-Jun
24 | Basic Design | [Categories Management] Update categories | basic design & common components of creating or updating category | 1 | In-progress |  | 06-Jun
25 | SRS | [Use Case Specifications] General user | List and complete use cases in general user | 1 | In-progress |  | 06-Jun
26 | SRS | [Use Case Specifications] Admin | List and complete use cases in admin | 1 | In-progress |  | 06-Jun
27 | SRS | Non-functional requirements | Show performance requirements, security requirement, software quality attributes | 1 | In-progress |  | 06-Jun
28 | SRS | Other requirements & Appendices | List other rules, common field, message configuration, error, template,.. | 1 | In-progress |  | 06-Jun