## Sprint Info
| Planning - Forecast |  |  |  |  | Actual
[5 empty] | PIC | Point | Release Point | Total ID
| Point Total |  | Points |  | MinhNHL | 0 | 0 | 0
| Working days of developer |  | Coding (day) |  | HungLC | 0 | 0 | 0
| Sprint 1 |  |  |  | HuyVH | 0 | 0 | 0
| (Forecast - Plan) Point Total | 0 | Points |  | SyNNV | 0 | 0 | 0
| Working days of developer | 8 | Coding (day) |  | QuanNM | 0 | 0 | 0
| (Forecast - Plan) AVG points/Member/Sprint | 0.0 | Points |  | DuyNM | 0 | 0 | 0
[5 empty] | PhuongHT | 0 | 0 | 0
[5 empty] | CanhNH | 0 | 0 | 0
[5 empty] | PhongNG | 0 | 0 | 0
[5 empty] | HaiNC | 0 | 0 | 0
[5 empty] | Total | 0 | 0 | 0
[6 empty] | Total |  | 0
No. | Module | Story | Description | Sprint | Status | PIC | DueDate | Point
1 | SRS | [Software Requirement Specification] Introduction | Write Introduction For Project | 2 | Done | DuyNM | 2024-06-21 | 0.30928
2 | SRS | [Software Requirement Specification] Software Project Management Plan | Write Software Project Management Plan For Project | 2 | Done | MinhNHL | 2024-06-21 | 0.30928
3 | SRS | [Software Requirement Specification] Usecase Overview & each of feature | Write Write Usecase Overview & each of feature Diagram | 2 | Done | QuanNM | 2024-06-21 | 0.30928
4 | SRS | [Software Requirement Specification] Software Design Description | Write Software Design Description | 2 | Process |  | 2024-06-21 | 0.30928
5 | SRS | [Use Case Specifications][UserManagement] Login (UC-1) | Use case specification of Login | 2 | Done | HaiNC | 2024-06-21 | 0.30928
6 | SRS | [Use Case Specifications][UserManagement] Logout (UC-2) | Use case specification of Logout | 2 | Done | HaiNC | 2024-06-21 | 0.30928
7 | SRS | [Use Case Specifications][UserManagement] Sign-up (UC-3) | Use case specification of Sign-up | 2 | Done | HaiNC | 2024-06-21 | 0.30928
8 | SRS | [Use Case Specifications][UserManagement] Reset password (UC-4) | Use case specification of Reset password | 2 | Done | HaiNC | 2024-06-21 | 0.30928
9 | SRS | [Use Case Specifications][UserManagement] View Dashboard (UC-5) | Use case specification of View Dashboard | 2 | Done | HaiNC | 2024-06-21 | 0.30928
10 | SRS | [Use Case Specifications][UserManagement] Retrives Course By Category List (UC-6) | Use case specification of Retrives Course By Category List | 2 | Done | HaiNC | 2024-06-21 | 0.30928
11 | SRS | [Use Case Specifications][UserManagement] Retrives Course By Category Filter (UC-7) | Use case specification ofRetrives Course By Category Filter | 2 | Done | HaiNC | 2024-06-21 | 0.30928
12 | SRS | [Use Case Specifications][StudentManagement] View Dashboard (UC-8) | Use case specification of View Dashboard For Student | 2 | Done | MinhNHL | 2024-06-21 | 0.30928
13 | SRS | [Use Case Specifications][StudentManagement] View Enrolled/Purchased Course (UC-9) | Use case specification of View Enrolled/Purchased Course | 2 | Done | MinhNHL | 2024-06-21 | 0.30928
14 | SRS | [Use Case Specifications][StudentManagement] View Profile (UC-10) | Use case specification of View Profile | 2 | Done | MinhNHL | 2024-06-21 | 0.30928
15 | SRS | [Use Case Specifications][StudentManagement] Edit Profile (UC-11) | Use case specification of Edit Profile | 2 | Done | MinhNHL | 2024-06-21 | 0.30928
16 | SRS | [Use Case Specifications][StudentManagement] View Settings (UC-12) | Use case specification of View Settings | 2 | Done | MinhNHL | 2024-06-21 | 0.30928
17 | SRS | [Use Case Specifications][StudentManagement] Edit Settings (UC-13) | Use case specification of Edit Settings | 2 | Done | MinhNHL | 2024-06-21 | 0.30928
18 | SRS | [Use Case Specifications][StudentManagement] View Privacy (UC-14) | Use case specification of View Privacy | 2 | Done | MinhNHL | 2024-06-21 | 0.30928
19 | SRS | [Use Case Specifications][StudentManagement] Edit Privacy (UC-15) | Use case specification of Edit Privacy | 2 | Done | MinhNHL | 2024-06-21 | 0.30928
20 | SRS | [Use Case Specifications][StudentManagement] View feedback history (UC-16) | Use case specification of View Feedback History | 2 | Done | MinhNHL | 2024-06-21 | 0.30928
21 | SRS | [Use Case Specifications][StudentManagement] Send feedback (UC-17) | Use case specification of Send Feedback | 2 | Done | MinhNHL | 2024-06-21 | 0.30928
22 | SRS | [Use Case Specifications][StudentManagement] Send request to become instructor(UC-18) | Use case specification of Send Request to Become Instructor | 2 | Done | PhuongHT | 2024-06-21 | 0.30928
23 | SRS | [Use Case Specifications][StudentManagement] View Course Details (UC-19) | Use case specification of View Course Details For Student | 2 | Done | PhuongHT | 2024-06-21 | 0.30928
24 | SRS | [Use Case Specifications][StudentManagement] Comment course (UC-20) | Use case specification of Comment Course | 2 | Done | PhuongHT | 2024-06-21 | 0.30928
25 | SRS | [Use Case Specifications][StudentManagement] View tracking of the course (UC-22) | Use case specification of View Tracking Of The Course | 2 | Done | PhuongHT | 2024-06-21 | 0.30928
26 | SRS | [Use Case Specifications][StudentManagement] Studying in course (UC-23) | Use case specification of Studying In Course | 2 | Done | PhuongHT | 2024-06-21 | 0.30928
27 | SRS | [Use Case Specifications][StudentManagement] View favorite course (UC-24) | Use case specification of View Favorite Course | 2 | Done | PhuongHT | 2024-06-21 | 0.30928
28 | SRS | [Use Case Specifications][StudentManagement] Save/Unsave favorite course (UC-25) | Use case specification of Save/UnSave Favorite Course | 2 | Done | PhuongHT | 2024-06-21 | 0.30928
29 | SRS | [Use Case Specifications][StudentManagement] View Notification (UC-26) | Use case specification of View Notification | 2 | Done | PhuongHT | 2024-06-21 | 0.30928
30 | SRS | [Use Case Specifications][StudentManagement] Follow/Unfollow instructor (UC-27) | Use case specification of Follow/Unfollow Instructor | 2 | Done | HaiNC | 2024-06-21 | 0.30928
31 | SRS | [Use Case Specifications][StudentManagement] View Follower (UC-28) | Use case specification of View Follower | 2 | Done | HaiNC | 2024-06-21 | 0.30928
32 | SRS | [Use Case Specifications][InstructorManagement] Authorization (UC-29) | Use case specification of Authorization Student | 2 | Done | SyNNV | 2024-06-21 | 0.30928
33 | SRS | [Use Case Specifications][InstructorManagement] View request history (UC-30) | Use case specification of View Request History | 2 | Done | SyNNV | 2024-06-21 | 0.30928
34 | SRS | [Use Case Specifications][InstructorManagement] Course dashboard (UC-31) | Use case specification of Course Dashboard | 2 | Done | SyNNV | 2024-06-21 | 0.30928
35 | SRS | [Use Case Specifications][InstructorManagement] View dashboard (UC-32) | Use case specification of View Dashboard | 2 | Done | SyNNV | 2024-06-21 | 0.30928
36 | SRS | [Use Case Specifications][InstructorManagement] View earning (UC-33) | Use case specification of View Earning | 2 | Done | SyNNV | 2024-06-21 | 0.30928
37 | SRS | [Use Case Specifications][InstructorManagement] Pay out (UC-34) | Use case specification of Payout | 2 | Done | SyNNV | 2024-06-21 | 0.30928
38 | SRS | [Use Case Specifications][InstructorManagement] View notification (UC-35) | Use case specification of View Notification | 2 | Done | SyNNV | 2024-06-21 | 0.30928
39 | SRS | [Use Case Specifications][InstructorManagement] Extends student (UC-36) | Use case specification of Extends use cases from student | 2 | Done | SyNNV | 2024-06-21 | 0.30928
40 | SRS | [Use Case Specifications][AdminManagement] Authorization (UC-37) | Use case specification of Authorization Admin | 2 | Done | DuyNM | 2024-06-21 | 0.30928
41 | SRS | [Use Case Specifications][AdminManagement] Role-Permission (UC-38) | Use case specification of Role-Permission | 2 | Done | DuyNM | 2024-06-21 | 0.30928
42 | SRS | [Use Case Specifications][AdminManagement] View Dashboard (UC-39) | Use case specification of View Dashboard | 2 | Done | DuyNM | 2024-06-21 | 0.30928
43 | SRS | [Use Case Specifications][AdminManagement] View List Of Students (UC-40) | Use case specification of View List Of Students | 2 | Done | DuyNM | 2024-06-21 | 0.30928
44 | SRS | [Use Case Specifications][AdminManagement] View List Of Instructors (UC-41) | Use case specification of View List Of Instructors | 2 | Done | DuyNM | 2024-06-21 | 0.30928
45 | SRS | [Use Case Specifications][AdminManagement] Block/Unblock Students & Instructors (UC-42) | Use case specification of View Block/Unblock Students & Instructors | 2 | Done | DuyNM | 2024-06-21 | 0.30928
46 | SRS | [Use Case Specifications][AdminManagement] Approve Student To Instructor (UC-43) | Use case specification of Approve Student To Instructor | 2 | Done | QuanNM | 2024-06-21 | 0.30928
47 | SRS | [Use Case Specifications][AdminManagement] Reject Student To Instructor (UC-44) | Use case specification of Reject Student To Instructor | 2 | Done | QuanNM | 2024-06-21 | 0.30928
48 | SRS | [Use Case Specifications][AdminManagement] View List Of Courses (UC-45) | Use case specification of View List Of Courses | 2 | Done | QuanNM | 2024-06-21 | 0.30928
49 | SRS | [Use Case Specifications][AdminManagement] Review Course (UC-46) | Use case specification of Review Course | 2 | Done | QuanNM | 2024-06-21 | 0.30928
50 | SRS | [Use Case Specifications][AdminManagement] Approve Course (UC-47) | Use case specification of Approve Course | 2 | Done | QuanNM | 2024-06-21 | 0.30928
51 | SRS | [Use Case Specifications][AdminManagement] Reject Course (UC-48) | Use case specification of Reject Course | 2 | Done | QuanNM | 2024-06-21 | 0.30928
52 | SRS | [Use Case Specifications][AdminManagement] Block/Unblock Course (UC-49) | Use case specification of Block/Unblock Course | 2 | Done | QuanNM | 2024-06-21 | 0.30928
53 | SRS | [Use Case Specifications][AdminManagement] Display/Undisplay comments (UC-50) | Use case specification of Display/Undisplay comments | 2 | Done | QuanNM | 2024-06-21 | 0.30928
54 | SRS | [Use Case Specifications][AdminManagement] View List Of Report Course/Comments (UC-51) | Use case specification of View List Of Report Course/Comments | 2 | Done | HungLC | 2024-06-21 | 0.30928
55 | SRS | [Use Case Specifications][AdminManagement] View List Of Feedbacks from User (UC-52) | Use case specification of View List Of Feedbacks From User | 2 | Done | HungLC | 2024-06-21 | 0.30928
56 | SRS | [Use Case Specifications][CategoryManagement] Create category (UC-53) | Use case specification of Create Category | 2 | Done | SyNNV | 2024-06-21 | 0.30928
57 | SRS | [Use Case Specifications][CategoryManagement] View category(UC-54) | Use case specification of View Category | 2 | Done | SyNNV | 2024-06-21 | 0.30928
58 | SRS | [Use Case Specifications][CategoryManagement] Update category(UC-55) | Use case specification of Update Category | 2 | Done | SyNNV | 2024-06-21 | 0.30928
59 | SRS | [Use Case Specifications][CategoryManagement] Delete category(UC-56) | Use case specification of Delete Category | 2 | Done | SyNNV | 2024-06-21 | 0.30928
60 | SRS | [Use Case Specifications][CourseManagement] View list course (UC-57) | Use case specification of View List Couse | 2 | Done | CanhNH | 2024-06-21 | 0.30928
61 | SRS | [Use Case Specifications][CourseManagement] Create course (UC-58) | Use case specification of Create Course | 2 | Done | CanhNH | 2024-06-21 | 0.30928
62 | SRS | [Use Case Specifications][CourseManagement] Update course (UC-59) | Use case specification of Update Course | 2 | Done | CanhNH | 2024-06-21 | 0.30928
63 | SRS | [Use Case Specifications][CourseManagement] Delete course (UC-60) | Use case specification of Delete Course | 2 | Done | CanhNH | 2024-06-21 | 0.30928
64 | SRS | [Use Case Specifications][CourseManagement] View chapter (UC-61) | Use case specification of View Chapter | 2 | Done | CanhNH | 2024-06-21 | 0.30928
65 | SRS | [Use Case Specifications][CourseManagement] Create chapter (UC-62) | Use case specification of Create Chapter | 2 | Done | CanhNH | 2024-06-21 | 0.30928
66 | SRS | [Use Case Specifications][CourseManagement] Update chapter (UC-63) | Use case specification of Update Chapter | 2 | Done | CanhNH | 2024-06-21 | 0.30928
67 | SRS | [Use Case Specifications][CourseManagement] Delete chapter (UC-64) | Use case specification of Delete Chapter | 2 | Done | CanhNH | 2024-06-21 | 0.30928
68 | SRS | [Use Case Specifications][CourseManagement] View quiz (UC-65) | Use case specification of View Quiz | 2 | Done | HuyVH | 2024-06-21 | 0.30928
69 | SRS | [Use Case Specifications][CourseManagement] Create quiz (UC-66) | Use case specification of Create Quiz | 2 | Done | HuyVH | 2024-06-21 | 0.30928
70 | SRS | [Use Case Specifications][CourseManagement] Update quiz (UC-67) | Use case specification of Update Quiz | 2 | Done | HuyVH | 2024-06-21 | 0.30928
71 | SRS | [Use Case Specifications][CourseManagement] Delete quiz (UC-68) | Use case specification of Delete Quiz | 2 | Done | HuyVH | 2024-06-21 | 0.30928
72 | SRS | [Use Case Specifications][CourseManagement] View question (UC-69) | Use case specification of View Question | 2 | Done | HuyVH | 2024-06-21 | 0.30928
73 | SRS | [Use Case Specifications][CourseManagement] Create question (UC-70) | Use case specification of Create Question | 2 | Done | HuyVH | 2024-06-21 | 0.30928
74 | SRS | [Use Case Specifications][CourseManagement] Update question (UC-71) | Use case specification of Update Question | 2 | Done | HuyVH | 2024-06-21 | 0.30928
75 | SRS | [Use Case Specifications][CourseManagement] Delete question (UC-72) | Use case specification of Delete Question | 2 | Done | HuyVH | 2024-06-21 | 0.30928
76 | SRS | [Use Case Specifications][CourseManagement] View answers (UC-73) | Use case specification of View Answer | 2 | Done | HungLC | 2024-06-21 | 0.30928
77 | SRS | [Use Case Specifications][CourseManagement] Create answer (UC-74) | Use case specification of Create Answer | 2 | Done | HungLC | 2024-06-21 | 0.30928
78 | SRS | [Use Case Specifications][CourseManagement] Update answer (UC-75) | Use case specification of Update Answer | 2 | Done | HungLC | 2024-06-21 | 0.30928
79 | SRS | [Use Case Specifications][CourseManagement] Delete answer (UC-76) | Use case specification of Delete Answer | 2 | Done | HungLC | 2024-06-21 | 0.30928
80 | SRS | [Use Case Specifications][CourseManagement] View certificate (UC-77) | Use case specification of View Certificate | 2 | Done | HuyVH | 2024-06-21 | 0.30928
81 | SRS | [Use Case Specifications][CourseManagement] Create certificate (UC-78) | Use case specification of Create Certificate | 2 | Done | HuyVH | 2024-06-21 | 0.30928
82 | SRS | [Use Case Specifications][CourseManagement] Update certificate (UC-79) | Use case specification of Update Certificate | 2 | Done | HuyVH | 2024-06-21 | 0.30928
83 | SRS | [Use Case Specifications][CourseManagement] View lecture (UC-80) | Use case specification of View Lecture | 2 | Done | HungLC | 2024-06-21 | 0.30928
84 | SRS | [Use Case Specifications][CourseManagement] Create lecture (UC-81) | Use case specification of Create Lecture | 2 | Done | HungLC | 2024-06-21 | 0.30928
85 | SRS | [Use Case Specifications][CourseManagement] Update lecture (UC-82) | Use case specification of Update Lecture | 2 | Done | HungLC | 2024-06-21 | 0.30928
86 | SRS | [Use Case Specifications][CourseManagement] Delete lecture (UC-83) | Use case specification of Delete Lecture | 2 | Done | HungLC | 2024-06-21 | 0.30928
87 | SRS | [Use Case Specifications][CourseManagement] Submit course (UC-84) | Use case specification of Submit Course | 2 | Done | CanhNH | 2024-06-21 | 0.30928
88 | SRS | [Use Case Specifications][CourseManagement] Report course (UC-85) | Use case specification of Report Course | 2 | Done | CanhNH | 2024-06-21 | 0.30928
89 | SRS | [Use Case Specifications][TransactionManagement] View My Wallet (UC-86) | Use case specification of View My Wallet | 2 | Done | PhongNG | 2024-06-21 | 0.30928
90 | SRS | [Use Case Specifications][TransactionManagement] Deposit Money to Wallet (UC-87) | Use case specification of Deposit Money To Wallet | 2 | Done | PhongNG | 2024-06-21 | 0.30928
91 | SRS | [Use Case Specifications][TransactionManagement] Add to Cart (UC-88) | Use case specification of Add To Cart | 2 | Done | PhongNG | 2024-06-21 | 0.30928
92 | SRS | [Use Case Specifications][TransactionManagement] Delete Course in Cart (UC-89) | Use case specification of Delete Course In Cart | 2 | Done | PhongNG | 2024-06-21 | 0.30928
93 | SRS | [Use Case Specifications][TransactionManagement] Purchase the entire course from the card (UC-90) | Use case specification of Purchase The Entire Course From The Card | 2 | Done | PhongNG | 2024-06-21 | 0.30928
94 | SRS | [Use Case Specifications][TransactionManagement] Buy one or more courses from the card (UC-91) | Use case specification of Buy One Or More Courses From The Card | 2 | Done | PhongNG | 2024-06-21 | 0.30928
95 | SRS | [Use Case Specifications][TransactionManagement] View Transaction History (UC-92) | Use case specification of View Transaction History | 2 | Done | PhongNG | 2024-06-21 | 0.30928
96 | SRS | [Use Case Specifications][TransactionManagement] Create Affiliate link (UC-93) | Use case specification of Create Affiliate Link | 2 | Done | PhongNG | 2024-06-21 | 0.30928
97 | SRS | [Use Case Specifications][TransactionManagement] Earning Affiliate marketing (UC-94) | Use case specification of Earning Affiliate marketing | 2 | Done | PhongNG | 2024-06-21 | 0.30928
98 | Database | [Database] Write Database | Design & Fix database | 2 | Process | All | 2024-06-21 | 2.6667
99 | FE | [FrontEnd-Dev] Design component & base | Design component & base | 2 | Process | All | 2024-06-21 | 2.6667
100 | BE | [BackEnd-Dev] Write API & Fetch API | Write API & Fetch API | 2 | Process | All | 2024-06-21 | 2.6667